## FY24-FY29_IID_Final SGR Program
Statewide SGR Bridge Project Selection (VDOT & Locality)
Draft Update to FY2024-FY2029 SYIP
Based on July 1, 2022 BrM_MN_INV data
Issued: | 2023-03-28
BASIC STRUCTURAL INFORMATION | [7 empty] | PROJECT COST ESTIMATES AND SCHEDULES
FED ID | District | VDOT / Locality | Owner | Route No. | Facility Carried | Facility Intersected | Functional Classification | UPC / Temp. UPC (If Applicable) | Project Scope | BROS Eligibility | Total Project Cost Estimate | PE Phase Cost Estimate | RW Phase Cost Estimate | CN Phase Cost Estimate | District Schedule Priority | PE Phase Schedule (Start) | PE Phase Schedule (End) | RW Phase Schedule (Start) | RW Phase Schedule (End) | CN Phase Schedule (Start) | CN Phase Schedule (End) | Notes to IID
22445 | 1-Bristol | Locality | 146-Norton | 0 | LAUREL AVENUE SW | BENGES BRANCH | Urban Local | T28080 | Bridge Rehabilitation - Superstructure Replacement | Yes | 1328645 | 193072 | 0 | 1135573 | n/a | 2025-08-01 | 2027-08-01 | n/a | n/a | 2027-08-01 | 2029-02-01
21663 | 2-Salem | Locality | 128-Roanoke | 11 | 13th St S.W. | VIRGINIA AVE O NS RWY | Urban Other Principal Arterial | T28081 | Bridge Rehabilitation - Superstructure Replacement | No | 5418679 | 0 | 14288 | 5404391 | n/a | n/a | n/a | 2025-08-01 | 2026-08-01 | 2026-08-01 | 4/81/2028
21367 | 4-Richmond | Locality | 127-Richmond | 0 | WALMSLEY BOULEVARD | GRINDALL CREEK | Urban Minor Arterial | T28059 | Culvert Replacement | No | 4241791 | 603895 | 831441 | 2806455 | n/a | 2026-11-01 | 2028-11-01 | 2028-11-01 | 2030-11-01 | 2030-11-01 | 2031-11-01
22113 | 5-Hampton Roads | Locality | 133-Suffolk | 616 | Roundtree Crescent | Cypress Swamp | Rural Local | T27934 | Culvert Replacement | Yes | 2226801.6 | 229864.64 | 73823.4 | 1923113.56 | n/a | 2025-08-01 | 2026-02-01 | 2025-12-01 | 2026-05-01 | 2026-06-01 | 2027-06-01
22301 | 8-Staunton | Locality | 136-Waynesboro | 0 | HOPEMAN PARKWAY | CSX RAILWAY | Urban Minor Arterial | T28028 | Bridge Replacement | No | 7643942 | 541753 | 47259 | 7054930 | n/a | 2025-08-01 | 2027-01-01 | 2027-01-01 | 2029-08-01 | 2029-08-01 | 2030-08-01
10993 | 1-Bristol | VDOT | State (VDOT) | 801 | Hawk Thorn Drive | STRAIGHT CREEK | Rural Local | T28064 | Bridge Replacement | Yes | 5322395.06 | 1250356.28 | 640925.78 | 3431113 | 1 | 2026-07-01 | 2027-07-01 | 2027-07-01 | 2028-07-01 | 2028-07-01 | 2029-12-01 | Smart Flag IF-2 has been requested and applied. Also planning to use a Design Waiver for a One-Lane Bridge.
16424 | 1-Bristol | VDOT | State (VDOT) | 624 | DRILL RD. | LEWIS CREEK | Rural Major Collector | T28069 | Bridge Replacement | No | 4508738 | 1172062 | 383965 | 2952711 | 3 | 2027-07-01 | 2029-04-09 | 2028-01-02 | 2029-04-09 | 2029-04-09 | 2031-07-15 | DEER expected to ensure this project is funded in this SYIP cycle.
19361 | 1-Bristol | VDOT | State (VDOT) | 605 | ROUTE 0605 | POWELL RIVER | Rural Local | T28063 | Bridge Rehabilitation - Superstructure Replacement | Yes | 6546067.5 | 1397645.46 | 61040.55 | 5087381.49 | 2 | 2026-07-01 | 2029-04-09 | 2028-05-17 | 2029-04-09 | 2029-04-09 | 2031-07-15 | Smart Flag IF-2 has been requested and applied.
4442 | 6-Fredericksburg | VDOT | State (VDOT) | 603 | COUNTYLINE CHURCH | TEMPLES MILL | Rural Minor Collector | T28045 | Bridge Replacement | Yes | 6004586.754 | 1191116.754 | 575678 | 4237792 | 1 | 2025-08-01 | 2028-08-01 | 2027-08-01 | 2028-08-01 | 2028-08-01 | 2030-08-01
10604 | 6-Fredericksburg | VDOT | State (VDOT) | 610 | PIEDMONT RD. | STREAM | Rural Local | T28046 | Bridge Replacement | Yes | 3648631.57 | 991793.57 | 537762 | 2119076 | 3 | 2025-08-01 | 2028-08-01 | 2027-08-01 | 2028-08-01 | 2028-08-01 | 2030-08-01
12780 | 6-Fredericksburg | VDOT | State (VDOT) | 611 | GILLIAM'S RD. | SWAMP | Rural Local | T28047 | Bridge Replacement | Yes | 2733220.88 | 930710.66 | 131139 | 1671371.22 | 2 | 2025-08-01 | 2028-08-01 | 2027-08-01 | 2028-08-01 | 2028-08-01 | 2030-08-01