GUIDELINES — For projects requiring steel price adjustments.

SP109-000120-01

VIRGINIA DEPARTMENT OF TRANSPORTATION

SPECIAL PROVISION FOR

PRICE ADJUSTMENT FOR STEEL

July 2, 2019

The Department will adjust monthly progress payments up or down as appropriate for cost changes in steel used on specific items of work identified in the Contract according to this provision. The master list of standard Pay Items the Department has determined are eligible for steel price adjustment is posted on the Construction Division website.

Items eligible for steel price adjustment for this Project will be shown on Form C-21C, included with the Proposal. Only items on the form C-21C will be eligible for steel price adjustment. Non-standard Pay Items will not be eligible for steel price adjustment unless such steel items are project-specific modifications of items normally eligible, are clearly and specifically identified by a separate and distinct steel Pay Item, and the quantities present on the Project constitute major items of the work.

The Bidder shall submit Form C-21C to the State Contract Engineer no later than 15 calendar days after the date of Award Recommendation letter to identify those pay items to which he chooses to apply steel price adjustment. The Bidder may choose to have steel price adjustment applied to any, all, or none of the eligible items shown on Form C-21C. However, the Bidder’s selection of items for steel price adjustment or non-selection (non-participation) may not be changed once he has submitted Form C-21C to the Department. Items the Bidder chooses for steel price adjustment must be designated by writing the word “Yes” in the column titled “Option” by each Pay Item chosen for adjustment. The Bidder’s designations on Form C-21C must be written in ink or typed, and signed by the Bidder to be considered complete. Items not properly designated, or designated with “No” or left blank on the Bidder’s C-21C form will automatically be removed from consideration for adjustment. No steel items will be eligible for steel price adjustment on this Project if the Bidder fails to return his Form C-21C on time.

Inventoried materials from the list of eligible items are specifically excluded for consideration. Items from the list of eligible items for which the Contractor has requested payment as Material on Hand according to Section 109.09 are also specifically excluded for consideration past the delivery date to the fabricator.

This provision shall apply only to material cost changes that occur between the date of the receipt of bids by the Department and the date the material is shipped to the fabricator. The Contractor, subcontractor, and supplier are required to place their purchase order for the steel items designated in this Contract for price adjustment within 30 calendar days after the date of execution of this Contract with the Department. The timeliness of the Contractor’s response is also to ensure the receipt of such items in a timely manner that shall not adversely affect his progress schedule or Contract completion date. The items shall further be specifically stored, labeled, or tagged, recognizable by color marking, and identifiable by Project for inspection and audit verification immediately upon arrival at the fabricator.

The Contractor shall submit documentation to the Engineer for all items listed in the Contract for which the Contractor is requesting a steel price adjustment. This documentation shall consist of material price quotes, bid papers, or other similar type of documentation satisfactory to the Department and support the completion of the form establishing the average price per pound for the eligible steel bid item. The Contractor must use the format as shown with this provision; no other format for presenting this information will be permitted. The Contractor shall certify that all items of documentation are original and were used in the computation of the amount bid for the represented eligible Pay Items for the month bids were opened. This documentation shall support the base line material price (“Base Price”) of the steel item only. No adjustment will be made for changes in other components of the item unit price, including, but not limited to, fabrication, shipping, storage, handling, and erection.

The Contractor will not be eligible for price adjustment of steel items if the Contractor fails to submit specifically required information (i.e., purchase order, price data, bill of lading, material information or other requested information) as noted herein.

Price adjustment of each qualifying item will only be considered if there is an increase or decrease in the cost of eligible steel materials in excess of 10 percent up to a maximum of 60 percent from the Base Price when compared with the latest published price index (“Price Index”) in effect at the time material is shipped to the fabricator.

The Price Index the Department is using is based on The U.S. Department of Labor, Bureau of Labor Statistics, Producers Price Index (PPI), which measures the average price change over time of the specific steel eligible item from the perspective of the seller of goods. The specific PPI to be used to adjust the price for the eligible VDOT steel items is shown on the list posted on the Department’s website. The PPI is subject to revision 4 months after original publication, therefore, price adjustments and payments will not be made until the index numbers are finalized.

Items under consideration for price adjustment will be compared to the steel category index items and the corresponding I.D. numbers in the master list of standard Pay Items eligible for steel price adjustment.

The price adjustment will be determined by comparing the percentage of change in index value beyond 10 percent above or below the index on the bid date to the index value on the date the steel material is shipped to the fabricator (Please see included sample examples). Weights and date of shipment must be documented by a bill of lading provided to the Department. The final price adjustment dollar value will be determined by multiplying this percent increase or decrease in the index (after 10%) by the represented quantity of steel shipped, by the Base Price per pound subject to the limitations herein.

Price increase/decrease will be computed as follows:

| A = B x P x Q |  |  |
| --- | --- | --- |
| Where; | A = | Steel price adjustment in lump sum dollars |
|  | B = | Average weighted price of steel submitted with bid on Project in $ per pound |
|  | P = | Adjusted percentage change in PPI average from shipping date to bid date minus 10% (0.10) threshold |
|  | Q = | Total quantity of steel in pounds shipped to fabricator for specific Project |

Delays to the work caused by steel shortages may be justification for a Contract time extension but will not constitute grounds for claims for standby equipment, extended office overhead, or other costs associated with such delays.

The Engineer will determine, and specify in the Change Order, the need for application of the adjustments herein to extra work on an individual basis.

This price adjustment is capped at 60 percent. This means the maximum “P” value for increase or decrease that can be used in the above equation is 50% (60%-10% threshold).

Calculations for price adjustment shall be shown separate from the monthly progress estimate and will not be included in the total cost of work for determination of progress or for extension of Contract time.

Any apparent attempt to unbalance bids in favor of items subject to price adjustment may result in rejection of the bid proposal.

| 20-Jan-05 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Steel Price Adjustment Sample Submission Form (All prices to be supported by project-specific quotes) |  |  |  |  |  |  |  |  |
|  |  |  |  | BID DATE |  |  | 28-Apr-04 |  |
| Bid Item 61720 High Strength Structural Steel |  |  |  |  |  |  |  |  |
|  | Supplier |  | Description of material | Unit price f.o.b supplier $/lbs |  | Quantity In lbs. | Price Extension | Date of Quote |
|  | XYZ mill |  | Structural beams Various sizes (see quote) | $0.28 |  | 1,200,000 | $336,000.00 | 21-Apr-04 |
|  | ABC distributing |  | Various channel & angle shapes (see quote) | $0.32 |  | 35,000 | $11,200.00 | 20-Apr-04 |
|  |  |  |  | Total |  | 1,235,000 | $347,200.00 |  |
|  |  |  |  | Average weighted price = |  |  | $0.2816 |  |
| Note: |  | All prices are to include any surcharges on materials quoted as if they are shipped in the month the bid is submitted. Vendors must include this surcharge along with their base price on their quotes. |  |  |  |  |  |  |

| 20-Jan-05 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Price Adjustment Sample Calculation (increase) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project bid on April 28, 2004. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project has 450,000 lb. of structural steel. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Orders placed in timely manner and according to contract. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contractor's *f.o.b. supplier price for the structural steel in bid is $0.2816 per pound. |  |  |  |  |  |  |  |  |  |  | *free on board |  |  |  |
| Adjusted** BLS Producers Price Index (PPI) most recently published average at time of bid is 139.6. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ** final change after 4 months |  |  |  |  |  |  |  |  |  |  |  |  |
| All steel shipped to fabricator in same month, October 2004. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Adjusted BLS PPI most recently published average for month of October is 161.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Adjustment formula is as follows: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | A = B X P X Q |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Where; |  | A = | Steel price adjustment in lump sum dollars |  |  |  |  |  |  |  |  |  |
|  |  |  |  | B = | Average weighted price of steel submitted with bid on Project in $ per pound |  |  |  |  |  |  |  |  |  |
|  |  |  |  | P = | Adjusted percentage change in PPI average from shipping date to bid date minus 10% (0.10) threshold |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Q = | Total quantity of steel shipped to fabricator in October 2004 for this Project in pounds |  |  |  |  |  |  |  |  |  |
|  |  | B = | $0.2816 |  |  |  |  |  |  |  |  |  |  |  |
|  |  | P = | (161.1- 139.6)/139.6 – 0.10 = 0.054 |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Q = | 450,000 lb. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | A = | 0.2816 x 0.054 x 450,000 |  |  |  |  |  |  |  |  |  |  |  |
|  |  | A = | $6,842.88 pay adjustment to Contractor |  |  |  |  |  |  |  |  |  |  |  |

| 20-Jan-05 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Price Adjustment Sample Calculation (decrease) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project bid on April 28, 2004. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project has 450,000 lb. of structural steel. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Orders placed in timely manner and according to contract. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contractor's *f.o.b. supplier price for structural steel in bid is $0.2816 per pound. |  |  |  |  |  |  |  |  |  |  | *free on board |  |  |  |
| Adjusted BLS Producers Price Index (PPI) most recently published average at time of bid is 156.6. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| All steel shipped to fabricator in same month, October 2004. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Adjusted BLS PPI most recently published average for month of October is 136.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Adjustment formula is as follows: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | A = B X P X Q |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Where; |  | A = | Steel price adjustment in lump sum dollars |  |  |  |  |  |  |  |  |  |
|  |  |  |  | B = | Average weighted price of steel submitted with bid on Project in $ per pound |  |  |  |  |  |  |  |  |  |
|  |  |  |  | P = | Adjusted percentage change in PPI average from shipping date to bid date minus 10% (0.10) threshold |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Q = | Total quantity of steel shipped to fabricator in October 2004 for this Project in pounds |  |  |  |  |  |  |  |  |  |
|  |  | B = | $0.2816 |  |  |  |  |  |  |  |  |  |  |  |
|  |  | P = | (156.6 – 136.3)/156.6 – 0.10 = 0.030 |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Q = | 450,000 lb. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | A = | 0.2816 x 0.030 x 450,000 |  |  |  |  |  |  |  |  |  |  |  |
|  |  | A = | $3,801.60 credit to Department |  |  |  |  |  |  |  |  |  |  |  |