Guidelines: Use when the project schedule allows adequate time for the Department to perfom the relocation work ahead of the contract ad date.  Determination should be made prior to the PAC meeting.

SP522-000260-00

VIRGINIA DEPARTMENT OF TRANSPORTATION

Special Provision for

PROTECTED Fish Species

DEPARTMENT PERFORMS RELOCATION

January 10, 2019

- Description

Stream Name is known to provide habitat for the Fish Common Name, a state or federally protected species. The Contractor shall take protective measures as described herein.

- Requirements

A Time of Year Restriction (TOYR) applies on all instream work from (DATE) to (DATE) with the exception of dewatering and other work within cofferdams, or as otherwise specified by the water quality permits issued for the project.

The Contractor shall install and remove cofferdams outside of the TOYR. The Contractor shall notify the Engineer at least 60 days before cofferdam placement, or a different notification timeframe as approved by the Engineer, and shall allow the Department’s biologists to perform fish relocation activities within all cofferdams. The Contractor shall not begin work within cofferdams until the fish relocation activities are completed, and the Engineer provides a written notice to proceed.

If the cofferdam overtops due to excessive stream flow after initial relocation efforts are complete, additional fish relocation will be required before subsequent dewatering activities. The Department will conduct additional fish relocation activities within 3 working days after receiving written notification of the overtopping.

- Measurement and Payment

No separate payment will be made for compliance with the requirements herein.