SQ105-000310-00 [formerly SQ105-030100-00]

GUIDELINES — Asphalt Schedules only (ST-SL-PM). {2007-SU100008B}

VIRGINIA DEPARTMENT OF TRANSPORTATION

SPECIAL PROVISION FOR

SECTION 105.03—AUTHORITIES OF PROJECT

PERSONNEL, COMMUNICATION AND DECISION MAKING

(Asphalt Schedules Only)

October 7, 2016

SECTION 105.03—Authorities of Project Personnel, Communication and Decision Making of the Specifications is amended to replace TABLE I-2A PROCESS GUIDELINES FOR REQUESTS GENERATED BY THE CONTRACTOR with the following:

| PROCESS GUIDELINES FOR REQUESTS GENERATED BY THE CONTRACTOR | Process if no resolution |  | Submit RDA or CCR | Submit Request for RDA | Submit RDA or CCR | Submit CCR | Claims process | 1Process initiated on the last business day of a week shall be acknowledged before 5 pm on the next VDOT business day. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Escalated process | Within | 7 days | 1 day1 | 2 days1 | 2 days1 | 7 days |  |
|  |  | By | DA or their designee* | DA or their designee | DA or their designee* | DA or their designee* | DA or their designee* |  |
|  | Normal resolution process | Within (calendar days) | ● Acknowledge: 3 days1 ● Accept or Return: 14 days ● Final Determination\Approve: 30 days or as outlined in Contract. | ● Confirmation: 1 day 1 | ● Action: 1 day 1 (or appropriate Action Plan) | ● Acknowledge: 1 day 1 ● Action: 2 days1 (or appropriate Action Plan) | ● Acknowledge: 3 days 1 ● Action: 30 days (45 days if federal oversight project) |  |
|  |  | By | Department’s Designated Project Manager | Department’s Appropriate field personnel | Department’s Designated Project Manager | Department’s Designated Project Manager | Departmnt’s Designated Project Manager |  |
|  | Situation |  | Contractor requests the Department’s review, acceptance or approval of shop drawings, materials data, test reports, project progress schedules, or other submittals required by Specifications or other Contract Documents. | Routine field issues, within the framework of the Contract, Contractor resolves through negotiation with the Department's field personnel. | Contractor needs the Department to supply information to provide better understanding of or to clarify a certain aspect of the work. | Contractor needs the Department to take certain action Contractor feels is required for proper completion of a portion of the Work or the project. | Contractor needs the Department to make an adjustment to the Contract because of excusable and/or compensable events, instructions that have or have not been given or other work that will require time and/or cost beyond that specified or envisioned within the original Contract. |  |
|  | Process |  | Submittal | Confirmation of Verbal Instruction (COVI) | Request for Information (RFI) | Request for Dept. Action (RDA) | Contract Change Request (CCR) |  |