SQ108-000210-00

SQ108-000210-00

GUIDELINES — For all NoVa Asphalt Schedule Work projects.

VIRGINIA DEPARTMENT OF TRANSPORTATION

SPECIAL PROVISION FOR

SECTION 108.02—LIMITATION OF OPERATIONS

October 7, 2016

SECTION 108.02—LIMITATIONS OF OPERATIONS of the Specifications is amended to include the following:

All work areas (and the limits thereof) and lane closures shall be in accordance with the Virginia Work Area Protection Manual and shall be approved by the Engineer.

Traffic control devices shall be kept clean, legible, and in proper working order at all times. The Contractor shall provide a person whose responsibility shall be to inspect and maintain signs, barricades, other channelizing devices, and lights while traffic is restricted due to the Contractor’s operations.

The Contractor shall not conduct operations requiring lane closures when the weather causes unsafe conditions for the traveling public as determined by the Engineer.

The Contractor shall submit lane and shoulder closure requests to the Engineer for approval seven (7) days in advance, stating the location, purpose, date, time, and duration of the closure. Confirmation shall be made twenty-four (24) hours before any scheduled lane closure and shall include a written reiteration of the proposed tasks and a list of materials, labor, and equipment to be used.

Complete road closures (for maximum of 20 minutes) require a seventy-two (72) hour advance confirmation for coordination. The Contractor shall provide adequate advance notification via variable message and required static signing for lane closures in accordance with the latest version of the Virginia Work Area Protection Manual. Once a closure is in place, work shall commence immediately and shall progress on a continuous basis to completion or to a designated time.

# All closures in the Express Lanes on either I-95 or I-495 shall be coordinated with the Express Lanes Operations Center at least five business days in advance using their Authorization to Work form (available from the Express Lanes Operations Center at (571) 419-6046.) Complete road closures on 95 Express Lanes and 495 Express Lanes shall not exceed 30 minutes.

No lane closure signing or other traffic disruptive work may be initiated outside the times specified. All signs, equipment, and materials shall be removed before the ending closure time indicated. No lane closures will be permitted outside the times detailed herein without the written authorization from the Engineer.

Extension of a lane closure time is not acceptable. Any changes to the allowable time periods above will require approval in accordance with the Contractor Proposed Alternative Traffic Control Plans special provision copied note. If the Contractor does not restore traffic lanes within the allowable time limits, the Contractor will not be allowed further lane closures until the reasons for the failure are evaluated and the Contractor can provide assurance that the causes have been corrected.

Restoration of traffic is defined as opening all travel lanes to traffic including the completion of all construction work, removing or relocating all work zone traffic control devices and signs to their approved site as determined by the VDOT Engineer, and removing all workers, materials and equipment from the roadway.

Failure to restore all lanes of traffic by the time limits defined herein will be handled as follows:

The Contractor will not be allowed further lane closures until the reasons for the previous failure are evaluated.

A formal submission as to the reasons for the failure to restore traffic lanes within the contract lane closure restrictions and the proposed corrective measures is to be provided to the VDOT Project Manager within two (2) days of the occurrence. A meeting with the District Construction Engineer or designee shall be required prior to the next scheduled lane closure at which the Contractor must be able to provide assurances to the Engineer that adjustments have been made to eliminate the operational causes of failure to restore all lanes of traffic within the time limits herein. No modifications to the Contract Time(s) will be granted or considered for these days.

When applicable, disincentives will be assessed on this project, or sections thereof, designated as subject to disincentives.

The Engineer may change any or all of the work hours stated below when such changes are in the best interest of the traveling public. The Engineer may monitor traffic conditions impacted by the work and make additional restrictions as necessary; i.e., terminate a lane closure early when excessive traffic backups occur or emergency situations dictate. Additional restrictions for other holidays or special local events may be necessary. In these situations, the Engineer will endeavor to inform the Contractor at the earliest opportunity and in no case less than 48 hours before the event.

Night Work

In areas where work will be performed during the hours of dusk or darkness, the Contractor shall furnish, place, and maintain lighting facilities capable of providing a minimum of 50 foot-candles of light for an area of approximately 15 feet by 15 feet with minimum of 5 foot-candles in the corners. The lights shall be arranged so as not to interfere with or impede traffic approaching the work sites from either direction or produce undue glare to property owners.

Lighting of work sites may be accomplished by using of any combination of portable floodlights or standard equipment lights, etc. that will provide the sufficient illumination for prosecution and inspection of the work, including, but not limited to, laying out and installing pavement markings and traffic loops. Unsupplemented lighting integral to or attached to working mobile equipment such as rollers, pavers, etc. will not be considered sufficient to meet the requirements of this specification.

The cost of providing lighting of the work site will be considered incidental and shall be included in the contract item unit prices of other work.

The Contractor shall provide sufficient fuel, spare lamps, generator, etc. to maintain the lighting of the work site. The Contractor shall use padding and shielding or locate mechanical and electrical equipment to minimize noise generated by lighting operations as directed by the Engineer. Noise generated by portable generators shall comply with all applicable Federal, State and Local environmental regulations.

The Contractor shall have a superintendent present during nighttime operations who will control all operations involved. The superintendent shall maintain contact with the Engineer and shall ensure that all actions required to correct any noted problems are taken promptly.

All private vehicles shall be parked outside the clear zone.

The Contractor shall review traffic control devices to ensure proper installation and working order, including monitoring of lights. The individual responsible for this review shall be qualified in accordance with Section 105.14 (a) of the Specifications.

Sound levels resulting from the Contractor’s operations shall conform to Section 107.16; (b), 3. of the Specifications The Contractor shall obtain all noise permits from the locality where the work is being performed as applicable.

Construction in Residential Subdivisions

Road work within residential subdivisions and/or cul-de-sac streets shall not be performed at night unless circumstances require night work and the Contractor obtains advance approval from the Engineer and conducts outreach to the residents that may be impacted to avoid noise issues.

Section 108.02 (b) Holidays of the Specifications is amended to include the following:

- Martin Luther King Jr. Day and Lee Jackson Day: As indicated below*.

- President’s Day: As indicated below*.

- Inauguration Day: From Noon on the preceding day until Noon on the following day, except as indicated below*.

- Easter: As indicated below*.

- September 11th: From Noon on the preceding day until Noon on the following day, except as indicated below*.

- Columbus Day: As indicated below*.

- Veteran’s Day: From Noon on the preceding day until Noon on the following day, except as indicated below*.

If the Holiday occurs on a Friday or Saturday: From Noon on the preceding Thursday to Noon on the following Monday.

If the Holiday occurs on a Sunday or Monday: From Noon on the preceding Friday to Noon on the following Tuesday.

*Note:

For low volume roadways (minor arterial), no lane closure is allowed during the holidays, but no restriction to the preceding day and the following day.

If an approved shoulder closure is required to protect from traffic hazards, no time restrictions will apply, but the Contractor shall continuously prosecute the work and remove the shoulder closure as soon as the hazard is addressed.