GUIDELINES — Where “$Provide amount” is shown, a justified dollar amount documented in the project file must be filled in. Where “Original Completion Date” is shown, the Completion Date in place when the project goes to advertisement must be filled in.

cn108-000411-02	EARLY COMPLETION INCENTIVE/DISINCENTIVE

Early Completion is defined as completing all of the Work as detailed in the Plans and Specifications to the Department's satisfaction for Final Acceptance, including, but not limited to, punch list, seeding, landscaping, and signal burn-in before Original Completion Date. This date will not change except for an extension of the Contract time limit for a Compensable Delay as defined by Section 109.05(e) of the Specifications.

The Department will pay an incentive of $Provide amount for each Calendar Day the Contractor completes the Work prior to the date shown above as adjusted by the Engineer for Compensable Delay. The incentive is capped at $Provide Amount.

If the Contractor does not complete the Work on or before date shown above as adjusted by the Engineer for Compensable Delay, the Department will assess a disincentive of $Provide amount per Calendar Day after the date shown above as adjusted by the Engineer for Compensable Delay that the Contractor does not complete the Work. The disincentive is capped at $Provide Amount.

The disincentive will be assessed, not as a penalty, but as agreed compensation for damages resulting from the Contractor's delay in completion of construction operations on the Department and road users.  The disincentive amount is calculated based on Department related traffic control and maintenance costs, detour costs, or daily road user costs, as applicable.

The Contractor waives any defense as to the validity of any disincentives stated in the Contract, the Specifications, or this Special Provision, and assessed by the Department against the Contractor on the grounds that such disincentives are void as penalties or are not reasonably related to actual damages.

9-10-19 (SPCN)