GUIDELINES —Where “$Provide amount” and **Month dd, yyyy** is shown, a justified dollar amount and date documented in the project file must be filled in.  This substantial completion is defined as “returning beneficial use to the Department.” Where “List Work Here” is shown, a list of work NOT REQUIRED for Substantial Completion must be filled in.

cn108-000413-02	SUBSTANTIAL COMPLETION INCENTIVE/DISINCENTIVE

The following terms are defined:

●	Substantial Completion is defined as completing the project to a point such that it can be safely and effectively used by the public or the Department for the purposes intended. Work not required for Substantial Completion includes List Work Here.

●	Substantial Completion Date is the date on or before which all work required for Substantial Completion must be completed such that the Contractor receives an incentive. This date will not change except for an extension of the Contract time limit for a Compensable Delay as defined by Section 109.05(e) of the Specifications.

The Substantial Completion Date for this project is **Month dd, yyyy**.  The Department will pay an incentive of $Provide amount for each Calendar Day before the Substantial Completion Date as adjusted by the Engineer for Compensable Delay that the Substantial Completion requirements are met.  The incentive is capped at $Provide Amount.

If the Substantial Completion requirements are not met on or before the Substantial Completion Date as adjusted by the Engineer for Compensable Delay, the Department will assess a disincentive of $Provide amount per Calendar Day after the Substantial Completion Date as adjusted by the Engineer for Compensable Delay that the Contractor does not achieve Substantial Completion. The disincentive is capped at $Provide Amount.

The disincentive will be assessed, not as a penalty, but as agreed compensation for damages resulting from the Contractor's delay.  The disincentive amount is calculated based on Department related traffic control and maintenance costs, detour costs, or daily road user costs, as applicable.

The Contractor waives any defense as to the validity of any disincentives stated in the Contract, the Specifications, or this Special Provision, and assessed by the Department against the Contractor on the grounds that such disincentives are void as penalties or are not reasonably related to actual damages.

9-10-19 (SPCN)