cq108-000141-01

GUIDELINES – 2020 slurry/latex schedule work only.  Use only with Districts (3)Lynchburg, (4)Richmond, (5)Hampton Roads, (6)Fredericksburg, (9)NoVa.

PAVING COMPLETION DATE and CONTRACT FIXED COMPLETION DATE — The Contractor shall complete all paving work no later than October 23, 2020.  For the purposes of this contract “Paving Completion” is defined as the completion of all paving work as detailed in the Contract including sealing cracks where required in the Contract; the replacement of damaged raised pavement markers; the removal of the protective covering, cleaning, and inspection of existing raised pavement markers; the complete placement of Emulsified Asphalt Slurry Seal, Latex Modified Emulsion Treatment, temporary construction pavement markings, and flexible temporary pavement markers (FTPMs); and the removal of temporary maintenance of traffic items to allow the traveling public to use the roadway in its final configuration with the exception of permanent pavement marking.  The contract fixed completion date shall be November 20, 2020.

The period of time between the paving completion date and the contract fixed completion date is to accommodate the completion of permanent pavement marking work according to the Special Provision for SECTION 704—PAVEMENT MARKINGS AND MARKERS included in the Contract and cleanup according to Section 105.16 of the Specifications as may be necessary for final completion and acceptance of the project.

9-25-19 (SPCN)